## Feuil1
OCHA ROWCA
INFORMATION MANAGEMENT SECTION
UNIT WORKPLAN 2014
UNIT | Project ID | Projets | STEP ID | STEPS | Jan | Feb | March | April | May | June | Jul | Aug | Sept | Oct | Nov | Dec
Websites and Web App | 1 | Performance Monitoring Dashboard | 1 | Script
Websites and Web App | 1 | Performanace Monitoring Dashboard | 2 | Draft 1
Websites and Web App | 1 | Performanace Monitoring Dashboard | 3 | Draft 2
Websites and Web App | 1 | Performanace Monitoring Dashboard | 4 | Final
Websites and Web App | 1 | Performanace Monitoring Dashboard | 5 | Maintenance / Improvement
Websites and Web App | 2 | E-Library and Secondary data review platform | 1 | Users management
Websites and Web App | 2 | E-Library and Secondary data review platform | 2 | Search documents
Websites and Web App | 2 | E-Library and Secondary data review platform | 3 | Mediamonitoring
Websites and Web App | 2 | E-Library and Secondary data review platform | 4 | Categorization
Websites and Web App | 2 | E-Library and Secondary data review platform | 5 | Tests and corrections
Websites and Web App | 2 | E-Library and Secondary data review platform | 6 | Deployment
Websites and Web App | 2 | E-Library and Secondary data review platform | 7 | Final
Websites and Web App | 2 | E-Library and Secondary data review platform | 8 | Maintenance / Improvement
Websites and Web App | 3 | Regional dashboard 2014 | 1 | Script
Websites and Web App | 3 | Regional dashboard 2014 | 2 | Draft 1
Websites and Web App | 3 | Regional dashboard 2014 | 3 | Draft 2
Websites and Web App | 3 | Regional dashboard 2014 | 4 | Final
Websites and Web App | 3 | Regional dashboard 2014 | 5 | Publications
Websites and Web App | 4 | Draft snapshot | 1 | Scripts
Websites and Web App | 4 | Draft snapshot | 2 | Drafts / thématiques
Websites and Web App | 4 | Draft snapshot | 3 | Publication (Ad hoc)
Data Management | 5 | Contact Directory | 1 | Concept note
Data Management | 5 | Contact Directory | 2 | Conceptualisation
Data Management | 5 | Contact Directory | 3 | Developpement
Data Management | 5 | Contact Directory | 4 | Tests et corrections
Data Management | 5 | Contact Directory | 5 | Final
Data Management | 5 | Contact Directory | 4 | User training
Data Management | 5 | Contact Directory | 6 | Maintenance / Improvement
Websites and Web App | 6 | Dynamic Prioritisation tool | 1 | Script
Websites and Web App | 6 | Dynamic Prioritisation tool | 2 | Draft 1
Websites and Web App | 6 | Dynamic Prioritisation tool | 3 | Draft 2
Websites and Web App | 6 | Dynamic Prioritisation tool | 4 | Final
Websites and Web App | 6 | Dynamic Prioritisation tool | 5 | Maintenance / Improvement
Websites and Web App | 7 | Dynamic Country Profile | 1 | Script
Websites and Web App | 7 | Dynamic Country Profile | 2 | Draft 1
Websites and Web App | 7 | Dynamic Country Profile | 3 | Draft 2
Websites and Web App | 7 | Dynamic Country Profile | 4 | Final
Websites and Web App | 7 | Dynamic Country Profile | 5 | Maintenance / Update
GIS | 8 | Geo Database | 1 | Concept
GIS | 8 | Geo Database | 2 | GIS Folder Management
GIS | 8 | Geo Database | 3 | Sahel Countries
GIS | 8 | Geo Database | 4 | Other Countries (15)
GIS | 8 | Geo Database | 5 | Update CODs on website
GIS | 9 | Reference maps approved by UN Cartography | 1 | Sahel Countries
GIS | 9 | Reference maps approved by UN Cartography | 2 | CAR, DRC
GIS | 9 | Reference maps approved by UN Cartography | 3 | Repubic Congo, Guinee Eq
GIS | 9 | Reference maps approved by UN Cartography | 4 | TB Filled (2countries)
GIS | 9 | Reference maps approved by UN Cartography | 5 | TB Filled (2countries)
GIS | 9 | Reference maps approved by UN Cartography | 6 | TB Filled (2countries)
GIS | 9 | Reference maps approved by UN Cartography | 7 | TB Filled (2countries)
GIS | 9 | Reference maps approved by UN Cartography | 8 | TB Filled (2countries)
GIS | 9 | Reference maps approved by UN Cartography | 9 | TB Filled (2countries)
GIS | 9 | Reference maps approved by UN Cartography | 9 | Complete 24 Countries
GIS | 10 | West and Central Africa weekly snapshot (liaise with PI) | 1 | Weekly update
GIS | 11 | Catalogue des cartes | 1 | Rename All maps
GIS | 11 | Catalogue des cartes | 2 | Physical Catalog (paper A4)
GIS | 11 | Catalogue des cartes | 3 | E Catalog (Web platform) => Web Application
GIS | 12 | Atlas par pays | 1 | Concept (+ vba?)
GIS | 12 | Atlas par pays | 2 | Template (Admin 0, Admin1 - 4)
GIS | 12 | Atlas par pays | 3 | Production Atlas
GIS | 13 | Registre des demandes | 1 | Developpement
GIS | 13 | Registre des demandes | 2 | Final
GIS | 13 | Registre des demandes | 3 | Update
GIS | 14 | Thematic maps (creation and update) | 1 | Ad hoc
GIS | 15 | Country snapshots (Mapping component) => Web Visualization | 1 | Ad hoc
GIS | 16 | Support teaching module on GIS applied to human contingencies | 1 | Module development (Draft 1)
GIS | 16 | Support teaching module on GIS applied to human contingencies | 2 | Module (Final)
GIS | 16 | Support teaching module on GIS applied to human contingencies | 3 | Training Lome University
Data Management | 17 | Sahel FTS Update | 1 | Setup Format 2014
Data Management | 17 | Sahel FTS Update | 2 | Update bi-weekly
Data Management | 18 | FOD registry | 1 | Conceptualisation
Data Management | 18 | FOD registry | 2 | Regular Update based on 2nd data review
Data Management | 18 | FOD registry | 3 | 2012-2013 Consolidation (MYR, HNO, SRPs)
Data Management | 18 | FOD registry | 4 | Local registry development
Data Management | 18 | FOD registry | 5 | Online registry development
Data Management | 19 | ROWCA Population Datasets | 1 | Collect RGPH (most recents for 24 Countries)
Data Management | 19 | ROWCA Population Datasets | 2 | Local population database (see 18.4)
Data Management | 19 | ROWCA Population Datasets | 3 | Online population database (see 18.5)
Data Management | 20 | E-Library and Secondary data review platform | 1 | Upload Douments
Data Management | 20 | E-Library and Secondary data review platform | 2 | Library Local web (see 2.7)
Data Management | 21 | Media Monitoring | 1 | EMM Feeds Monitoring
Data Management | 21 | Media Monitoring | 2 | EMM Feeds Monitoring (Final)
Data Management | 21 | Media Monitoring | 3 | EMM Feeds Monitoring (Improvement)
Data Management | 22 | Risk Monitoring | 1 | Conceptualisation (link with 18.5 and 21.2)
Data Management | 22 | Risk Monitoring | 2 | Exploring Data sources
Data Management | 22 | Risk Monitoring | 3 | Deployment
Data Management | 22 | Risk Monitoring | 4 | Maintenance / Improvement